## Sheet1
Project Name | Randford bank
Module | Admin
Prepared By | Ravi
Prepared Date | 2024-06-13
S.No | Requirement Spec References | Clarification Required | Clarification Provided | Clarification Provided By
1 | Admin FRS /Req 3.4/Page 17 | As per task flow diagram when admin try to delete branch system check for dependencies is not clear | We cannot delete a branch which is having cutomers and Transactions in it. We need to run a migration job to transfer all transactions to new branch. | Riyaz